## Overview
Submission Workbook — SAC Nitrate-Reduction DFT Benchmark
Recommended venue | Computational Materials Science
Article framing | Reproducibility-stage periodic-DFT benchmark and production-readiness framework
Repository | https://github.com/hassanraza147/single-atom-nitrate-reduction-dft
Latest repository commit | 78fed93
Key evidence boundary | No accepted catalyst ranking, nitrate adsorption dataset, complete mechanism, selectivity, limiting potential, or electrochemical stability result is currently available.
Workbook contents
Submission Checklist
Claim Evidence
Run Status
Production Manifest
Convergence

## Submission Checklist
Item | Required action | Status | Author action
Main manuscript | Upload Word/PDF review file with embedded components | Prepared | Confirm final author list and upload
Highlights | Paste five prepared highlights | Prepared | Review wording
Graphical abstract | Use workflow graphic only; do not imply unsupported performance | Specification prepared | Create/approve optional graphic
Supporting Information | Upload as separate supplementary file | Prepared | Convert to portal-accepted format if required
Cover letter | Address editor and name Computational Materials Science | Prepared | Insert date and corresponding-author details
Research-data statement | Include repository and VASP licensing boundary | Prepared | Confirm archival DOI if required
Funding statement | Provide actual funding or no-specific-funding statement | Pending author input | Complete accurately
Competing interests | Provide actual declaration | Pending author input | Complete accurately
Author contributions | Provide actual contribution statement | Pending author input | Complete accurately
Submission declaration | Confirm originality and no concurrent submission | Pending author input | Confirm before upload

## Claim Evidence
claim_id | claim | claim_class | evidence_path | status | allowed_wording
C01 | The project generated 36 bare/support structures and 60 adsorbate starting structures | direct | data/geometry_audit.txt;data/adsorbate_geometry_audit.txt | verified | generated and audited starting inputs
C02 | All generated structures pass current geometric checks | direct | data/geometry_audit.txt;data/adsorbate_geometry_audit.txt | verified | passed the defined file/geometry audit
C03 | The compact benchmark has 11 calculations | direct | data/convergence/convergence.csv | verified | 11-case compact benchmark
C04 | Cutoff k-point and vacuum families require refinement | derived | data/convergence/convergence_analysis.md | verified | diagnostic ranges require refinement
C05 | The closed-shell graphene spin comparison is stable | derived | data/convergence/convergence.csv | verified | stable within the tested graphene benchmark
C06 | GPAW periodic execution is verified | direct | data/gpaw_runs;ENVIRONMENT.md | verified | periodic GPAW execution was verified
C07 | The 30 SACs are the best nitrate-reduction catalysts | unsupported | none | not_allowed | not claimed
C08 | Nitrate adsorption energies are available for the 30 SACs | unsupported | none | not_allowed | not claimed
C09 | A complete ammonia pathway and transition states are available | unsupported | none | not_allowed | not claimed
C10 | The workflow is required before catalyst ranking | literature-supported plus project-derived | dft_protocol.md;article_writing_research.md | qualified | required by the stated reproducibility design
C11 | The YouTube video validates chemistry claims | unsupported | none | not_allowed | used only as communication guidance
C12 | The manuscript is suitable as a benchmark/workflow paper | interpretive | article_redesign_spec.md;comprehensive_audit_report.md | qualified | positioned as a reproducibility-stage benchmark
C13 | Table 1 reports the proposed matched support/metal matrix | design | data/design specification and manuscript Table 1 | verified | proposed input matrix only
C14 | Table 2 reports the audited structure inventory | direct | data/geometry_audit.txt;data/adsorbate_geometry_audit.txt and manuscript Table 2 | verified | input and geometry audit only
C15 | Table 3 reports executed calculation status | direct | data/parsed_run_status.csv and manuscript Table 3 | verified | diagnostic execution status only
C16 | Table 4 reports family-wise convergence diagnostics | derived | data/convergence/convergence.csv;data/convergence/convergence_analysis.md and manuscript Table 4 | verified | absolute-energy diagnostic only
C17 | Figure 1 is generated from the archived convergence CSV | direct | data/convergence/convergence.csv;scripts/plot_convergence.py;figures/final/convergence_benchmark.png | verified | diagnostic plot not catalytic ranking
C18 | Equations 1 and 2 define bookkeeping conventions | methodological | manuscript/manuscript.md | verified | definitions not calculated results
C19 | Table 5 classifies limitations and repairs | derived | limitation_audit.md and manuscript Table 5 | verified | repair and evidence-boundary synthesis only
C20 | The project has no accepted catalyst ranking | unsupported | data/parsed_run_status.csv;PROJECT_STATUS.md | verified | ranking not available or claimed

## Run Status
run_dir | structure | energy_before_eV | energy_after_eV | converged | optimizer_steps | acceptance
data/gpaw_runs/Fe_MoS2_pw | structures/initial/ase_generated/MoS2_Svac/Fe@MoS2_Svac.vasp | -306.601389979665 | -308.047546302374 | False | 5 | DIAGNOSTIC_ONLY
data/gpaw_runs/Fe_graphene | structures/initial/ase_generated/graphene_N4/Fe@graphene_N4.vasp | -262.728306101863 | -265.130677384628 | True | 12 | DIAGNOSTIC_ONLY
data/gpaw_runs/Fe_graphene_lcao_sz | structures/initial/ase_generated/graphene_N4/Fe@graphene_N4.vasp | -199.182243545699 | -201.959605186400 | False | 5 | DIAGNOSTIC_ONLY
data/gpaw_runs/Fe_graphene_pw | structures/initial/ase_generated/graphene_N4/Fe@graphene_N4.vasp | -7.712643246012 | -13.795566612768 | False | 5 | DIAGNOSTIC_ONLY

## Production Manifest
campaign_id | stage | sac_id | adsorbate | support | input_structure | required_checks | status
bare_Au@MoS2_Svac | bare_SAC_optimisation | Au@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Au@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Co@MoS2_Svac | bare_SAC_optimisation | Co@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Co@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Cu@MoS2_Svac | bare_SAC_optimisation | Cu@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Cu@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Fe@MoS2_Svac | bare_SAC_optimisation | Fe@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Fe@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Ni@MoS2_Svac | bare_SAC_optimisation | Ni@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Ni@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Pd@MoS2_Svac | bare_SAC_optimisation | Pd@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Pd@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Pt@MoS2_Svac | bare_SAC_optimisation | Pt@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Pt@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Rh@MoS2_Svac | bare_SAC_optimisation | Rh@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Rh@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Ru@MoS2_Svac | bare_SAC_optimisation | Ru@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Ru@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Zn@MoS2_Svac | bare_SAC_optimisation | Zn@MoS2_Svac | none | MoS2_Svac | structures/initial/ase_generated/MoS2_Svac/Zn@MoS2_Svac.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Au@gC3N4_N4 | bare_SAC_optimisation | Au@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Au@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Co@gC3N4_N4 | bare_SAC_optimisation | Co@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Co@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Cu@gC3N4_N4 | bare_SAC_optimisation | Cu@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Cu@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Fe@gC3N4_N4 | bare_SAC_optimisation | Fe@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Fe@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Ni@gC3N4_N4 | bare_SAC_optimisation | Ni@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Ni@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Pd@gC3N4_N4 | bare_SAC_optimisation | Pd@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Pd@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Pt@gC3N4_N4 | bare_SAC_optimisation | Pt@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Pt@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Rh@gC3N4_N4 | bare_SAC_optimisation | Rh@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Rh@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Ru@gC3N4_N4 | bare_SAC_optimisation | Ru@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Ru@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Zn@gC3N4_N4 | bare_SAC_optimisation | Zn@gC3N4_N4 | none | gC3N4_N4 | structures/initial/ase_generated/gC3N4_N4/Zn@gC3N4_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Au@graphene_N4 | bare_SAC_optimisation | Au@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Au@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Co@graphene_N4 | bare_SAC_optimisation | Co@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Co@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Cu@graphene_N4 | bare_SAC_optimisation | Cu@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Cu@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Fe@graphene_N4 | bare_SAC_optimisation | Fe@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Fe@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Ni@graphene_N4 | bare_SAC_optimisation | Ni@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Ni@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Pd@graphene_N4 | bare_SAC_optimisation | Pd@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Pd@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Pt@graphene_N4 | bare_SAC_optimisation | Pt@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Pt@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Rh@graphene_N4 | bare_SAC_optimisation | Rh@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Rh@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Ru@graphene_N4 | bare_SAC_optimisation | Ru@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Ru@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
bare_Zn@graphene_N4 | bare_SAC_optimisation | Zn@graphene_N4 | none | graphene_N4 | structures/initial/ase_generated/graphene_N4/Zn@graphene_N4.vasp | multi_spin;force_convergence;alternative_placement;raw_archive;stability_followup | NOT_RUN
screen_Au@MoS2_Svac__H | adsorbate_screening | Au@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Au@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Au@MoS2_Svac__NO3 | adsorbate_screening | Au@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Au@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Co@MoS2_Svac__H | adsorbate_screening | Co@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Co@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Co@MoS2_Svac__NO3 | adsorbate_screening | Co@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Co@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Cu@MoS2_Svac__H | adsorbate_screening | Cu@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Cu@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Cu@MoS2_Svac__NO3 | adsorbate_screening | Cu@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Cu@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Fe@MoS2_Svac__H | adsorbate_screening | Fe@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Fe@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Fe@MoS2_Svac__NO3 | adsorbate_screening | Fe@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Fe@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ni@MoS2_Svac__H | adsorbate_screening | Ni@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Ni@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ni@MoS2_Svac__NO3 | adsorbate_screening | Ni@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Ni@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pd@MoS2_Svac__H | adsorbate_screening | Pd@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Pd@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pd@MoS2_Svac__NO3 | adsorbate_screening | Pd@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Pd@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pt@MoS2_Svac__H | adsorbate_screening | Pt@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Pt@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pt@MoS2_Svac__NO3 | adsorbate_screening | Pt@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Pt@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Rh@MoS2_Svac__H | adsorbate_screening | Rh@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Rh@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Rh@MoS2_Svac__NO3 | adsorbate_screening | Rh@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Rh@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ru@MoS2_Svac__H | adsorbate_screening | Ru@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Ru@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ru@MoS2_Svac__NO3 | adsorbate_screening | Ru@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Ru@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Zn@MoS2_Svac__H | adsorbate_screening | Zn@MoS2_Svac | H | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Zn@MoS2_Svac__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Zn@MoS2_Svac__NO3 | adsorbate_screening | Zn@MoS2_Svac | NO3 | MoS2_Svac | structures/initial/adsorbates/MoS2_Svac/Zn@MoS2_Svac__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Au@gC3N4_N4__H | adsorbate_screening | Au@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Au@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Au@gC3N4_N4__NO3 | adsorbate_screening | Au@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Au@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Co@gC3N4_N4__H | adsorbate_screening | Co@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Co@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Co@gC3N4_N4__NO3 | adsorbate_screening | Co@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Co@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Cu@gC3N4_N4__H | adsorbate_screening | Cu@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Cu@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Cu@gC3N4_N4__NO3 | adsorbate_screening | Cu@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Cu@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Fe@gC3N4_N4__H | adsorbate_screening | Fe@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Fe@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Fe@gC3N4_N4__NO3 | adsorbate_screening | Fe@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Fe@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ni@gC3N4_N4__H | adsorbate_screening | Ni@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Ni@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ni@gC3N4_N4__NO3 | adsorbate_screening | Ni@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Ni@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pd@gC3N4_N4__H | adsorbate_screening | Pd@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Pd@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pd@gC3N4_N4__NO3 | adsorbate_screening | Pd@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Pd@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pt@gC3N4_N4__H | adsorbate_screening | Pt@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Pt@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pt@gC3N4_N4__NO3 | adsorbate_screening | Pt@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Pt@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Rh@gC3N4_N4__H | adsorbate_screening | Rh@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Rh@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Rh@gC3N4_N4__NO3 | adsorbate_screening | Rh@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Rh@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ru@gC3N4_N4__H | adsorbate_screening | Ru@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Ru@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ru@gC3N4_N4__NO3 | adsorbate_screening | Ru@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Ru@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Zn@gC3N4_N4__H | adsorbate_screening | Zn@gC3N4_N4 | H | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Zn@gC3N4_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Zn@gC3N4_N4__NO3 | adsorbate_screening | Zn@gC3N4_N4 | NO3 | gC3N4_N4 | structures/initial/adsorbates/gC3N4_N4/Zn@gC3N4_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Au@graphene_N4__H | adsorbate_screening | Au@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Au@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Au@graphene_N4__NO3 | adsorbate_screening | Au@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Au@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Co@graphene_N4__H | adsorbate_screening | Co@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Co@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Co@graphene_N4__NO3 | adsorbate_screening | Co@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Co@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Cu@graphene_N4__H | adsorbate_screening | Cu@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Cu@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Cu@graphene_N4__NO3 | adsorbate_screening | Cu@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Cu@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Fe@graphene_N4__H | adsorbate_screening | Fe@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Fe@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Fe@graphene_N4__NO3 | adsorbate_screening | Fe@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Fe@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ni@graphene_N4__H | adsorbate_screening | Ni@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Ni@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ni@graphene_N4__NO3 | adsorbate_screening | Ni@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Ni@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pd@graphene_N4__H | adsorbate_screening | Pd@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Pd@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pd@graphene_N4__NO3 | adsorbate_screening | Pd@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Pd@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pt@graphene_N4__H | adsorbate_screening | Pt@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Pt@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Pt@graphene_N4__NO3 | adsorbate_screening | Pt@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Pt@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Rh@graphene_N4__H | adsorbate_screening | Rh@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Rh@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Rh@graphene_N4__NO3 | adsorbate_screening | Rh@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Rh@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ru@graphene_N4__H | adsorbate_screening | Ru@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Ru@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Ru@graphene_N4__NO3 | adsorbate_screening | Ru@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Ru@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Zn@graphene_N4__H | adsorbate_screening | Zn@graphene_N4 | H | graphene_N4 | structures/initial/adsorbates/graphene_N4/Zn@graphene_N4__H.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN
screen_Zn@graphene_N4__NO3 | adsorbate_screening | Zn@graphene_N4 | NO3 | graphene_N4 | structures/initial/adsorbates/graphene_N4/Zn@graphene_N4__NO3.vasp | charge_convention;dipole_correction;solvation_sensitivity;spin_check;raw_archive | NOT_RUN

## Convergence
family | label | cutoff_eV | kmesh | vacuum_A | spinpol | energy_eV
cutoff | 150 | 150 | 1x1x1 | 12.0 | False | -9.954667317578
cutoff | 250 | 250 | 1x1x1 | 12.0 | False | -52.554960853428
cutoff | 350 | 350 | 1x1x1 | 12.0 | False | -63.439445201602
kmesh | 1x1x1 | 250 | 1x1x1 | 12.0 | False | -52.554960853428
kmesh | 2x2x1 | 250 | 2x2x1 | 12.0 | False | -61.136436670413
kmesh | 3x3x1 | 250 | 3x3x1 | 12.0 | False | -60.934674325568
vacuum | 10.0 | 250 | 1x1x1 | 10.0 | False | -52.091381249578
vacuum | 15.0 | 250 | 1x1x1 | 15.0 | False | -52.384033544891
vacuum | 20.0 | 250 | 1x1x1 | 20.0 | False | -52.130281275265
spin | False | 250 | 1x1x1 | 15.0 | False | -52.384033544891
spin | True | 250 | 1x1x1 | 15.0 | True | -52.384033544895